## Sheet1
level | task | 工時 | 起始日期 | 結束日期 | 參與者
| Overall | 16 weeks | 2020-10-06 | 2021-01-19 | all members
1 | reverse engineering | 7 weeks | 2020-10-06 | 2020-11-22 | all members
1.1 | code tracing | 3 weeks | 2020-10-06 | 2020-11-01 | all members
1.1.1 | high level modules' survey | 2 weeks | 2020-10-06 | 2020-10-11 | all members
1.1.2 | DispatcherServlet | 2 weeks | 2020-10-11 | 2020-10-25 | all members
1.1.3 | HandlerMapping | 2 weeks | 2020-10-11 | 2020-10-25 | 林慶珠、吳崇維
1.1.4 | HandlerAdapter | 2 weeks | 2020-10-11 | 2020-10-25 | 王廷峻、王俊翔
1.1.5 | View/ViewResolver | 2 weeks | 2020-10-11 | 2020-10-25 | 蔡昀達、王郁婷、陳熙、 林柏劭、黃柏諭
1.1.6 | Miscellaneous modules and code | 3 weeks | 2020-10-11 | 2020-11-03 | all members
1.2 | Class diagram | 4 weeks | 2020-10-11 | 2020-11-08 | all members
1.3 | refactoring | 2 weeks | 2020-11-08 | 2020-11-22 | all members
2 | reengineering | 5 weeks | 2020-11-23 | 2020-12-28 | all members
2.1 | 評估 spring mvc 中使用的外部套件 python 是否支援 | 1 week | 2020-11-23 | 2020-11-30 | all members
2.2 | Python 重現與 Spring MVC 高度依賴的外部 module | 4 weeks | 2020-11-30 | 2020-12-28 | all members
2.3 | Python 重現 | 4 weeks | 2020-11-30 | 2020-12-28 | all members
3 | Testing | 4 weeks | 2020-12-29 | 2021-01-19 | all members
3.1 | Review testing code in spring MVC | 1 week | 2020-12-29 | 2021-01-04 | all members
3.2 | Unit Test | 1 week | 2021-01-05 | 2021-01-12 | all members
3.3 | Generate simplified testing code | 1 weeks | 2021-01-12 | 2021-01-19 | all members